## 0. Summary
FXR90 REST API - Review Fix List
Reviewed by | Mayur Bhandare - REVIEWER. He raised 35 of the 36 issues in a screen-shared walkthrough of the Swagger documentation. Manoharan Balakrishnan co-raised #4 (inventory protocol enum, 00:07:11) and maintains a parallel document that must be kept in sync. All fixes go back to Mayur for sign-off.
Source | Review call transcript - Mayur Bhandare and Manoharan Balakrishnan.
File to edit | RestAPI/FXR90-rest-api.yaml (plus RestAPI/operation_descriptions/ for wording-only items)
COUNTS
Confirmed issues | 36 (tab 1)
Open / to verify | 10 (tab 2)
Owner split | Doc 13 ¦ Dev 13 ¦ Dev + Doc 10
ALREADY DONE - VERIFY AND CLOSE
#4 inventoryProtocol enum | The enum is ALREADY [GEN2X, GEN2, HYBRID] in both GetModeResponse and SetModeRequest. Only the EXAMPLES are wrong - that is #2. Do not redo the enum.
#16 model enum | FXR90 IS already present: [FXR90, FX7500, FX9600, ATR7000, FXR60]. The only open question is whether to strip the other four models. Ask Mayur.
ITEMS THAT MERGE - DO THEM TOGETHER
#11 + #20 | Both are the /cloud/stack-led path. One fix.
#12 + #34 | Both are removing GCP from cloud config. One fix.
#32 + #33 + #34 roll up into #36 | All are the Config schema. Do #36 as one pass rather than four.
#27 + #28 + #29 + #30 + #31 | All are Operating Mode (GET+PUT /cloud/mode). This is the single biggest chunk of work - do it as one pass. #30 is the guardrail: do NOT duplicate transmitPower, antennaStopCondition, query, delayBetweenAntennaCycles, reportFilter, which already exist.
EASIEST WINS - START HERE
#19 App LED blue | SetAppledRequest.color.enum - delete 'blue'. One line. Keep blue in SetStackledRequest.
#2 Gen2 example | Three examples on /cloud/mode currently say GEN2X. Change to GEN2. Highest customer impact of any item on the list.
#32 XML | GetConfigResponse.xml and SetConfigMqttRequest.xml - both present, both deletable.
#31 stray fields | SetModeRequest has stray 'component', 'payload', 'linkProfile'. Delete.
NEXT ACTION (agreed with Mayur, 01:02:21)
Gating item | Update the NTP server description FIRST as a single sample, get Mayur's review, and only then roll the template out.
Owed to Manoharan | 00:15:09 - he maintains a parallel document and asked for the change list in Excel or Word so he can mirror it. This workbook is that artifact. Send it.
WHICH FILE DO I EDIT?
MD FILE(S) TO UPDATE | RestAPI/operation_descriptions/*.md - wording, notes, tables, 'Supported X' rows. Green column.
YAML UPDATE NEEDED | RestDeveloperfile.yaml - schema, enums, properties, examples. Orange column. Grey = no schema change needed.
Both columns filled | Most items need BOTH - a schema change AND the description updated to match. That is issue #25 in a nutshell.
MD only (no schema change) | #10, #17, #30 - pure wording.
YAML only (no .md change) | #4, #7, #14 - schema/examples only.
COMPLEXITY BREAKDOWN
Simple | 15 items - self-contained edits, no unknowns. Includes #2, the highest-impact item on the list. Roughly half the list can be done today.
Medium | 10 items - mechanical but touch many places, or need one fact confirmed.
Complex | 7 items (11 counting the merged ones) - real schema design work, or scope you cannot bound yet.
Where the effort actually is | Operating Mode (#27, #28, #29, #31) = getMode.md + setMode.md + the mode schemas. That is MOST of the real work. Everything else is small by comparison.
BLOCKED - SEND THIS TO MAYUR FIRST
8 items are blocked on others, not on you | #3 (what verbose excludes) #8 (the payload) #9 (expandAll) #12 (MQTTGC name) #15 (log levels) #17 (which server) #23 (powerNegotiation spelling) #31 (dock door / ATR). Also #16 (strip the model enum?) and #22/#26 need dev input. Send these BEFORE starting, or you will finish the easy 15 and stall.
VERIFICATION - 14 Jul 2026 (against the generated spec)
FIXED | 10 of 36 - #2 #4 #5 #14 #18 #19 #27 #28 #29 #33
PARTIAL | 2 - #24 (network fields look broad, need sign-off), #31 (directionality gone, but component/payload/linkProfile remain)
NOT FIXED | 23 of 36 - everything else
No edit needed | 1 - #30 is a guardrail only
Biggest win | #28 - selects, accesses, radioStartConditions, radioStopConditions, rssiFilter and filter are now REAL properties on operatingMode.v1, not example-only. With #27 and #29 that closes most of the Operating Mode project.
Still blocked on Mayur | #3 (what verbose:true excludes) #8 (the WebSocket payload) #9 (expandAll) #12/#34 (exact MQTTGC name) #17 (which 'server') #31 (dock door / ATR)
Still blocked on dev | #15 (which log levels are real) #22 (correct powerSource values) #23 (powerNegotiation enum spelling) #26 (exact readerLocation name)
Quick wins left | #16 strip 4 models from the enum #19 done #32 delete two xml properties #21 add an 'always empty' note #13 paste Mayur's sentence #31 delete 3 stray fields

## 1. Fix List
FXR90 - REVIEW FIX LIST (36 items, mapped to endpoint + schema field)
# | Area | Problem identified | Required action | Raised by | ENDPOINT TO FIX | SCHEMA / FIELD TO EDIT | MD FILE(S) TO UPDATE (RestAPI/operation_descriptions/) | YAML UPDATE NEEDED? (RestDeveloperfile.yaml) | Owner | Time | Status | Notes | Complexity | Blocked on | VERIFIED IN SPEC (14 Jul) | EVIDENCE IN FXR90-rest-api.yaml
1 | Docs - global | Documentation links are broken. | Repair or replace the links. | Mayur Bhandare | (global) | info.description, externalDocs.url, and any links inside operation descriptions | ALL 70 .md files (any embedded links) | YES - info.description + externalDocs.url | Doc | 00:00:14 | NOT FIXED |  | Simple |  | NOT FIXED | info.description + externalDocs.url unchanged. No link audit done.
2 | Get/Set Mode | Example shows Gen2X, but the actual/default mode is Gen2. | Change the default example to Gen2. REASON (Mayur 00:08:19): 'Whatever we have given, they'll copy, they'll paste, they will execute. After that they will raise SPR, like we are not able to write tags.' | Mayur Bhandare | GET /cloud/mode, PUT /cloud/mode | The EXAMPLES only, not the schema: paths./cloud/mode.get.responses.200.example.inventoryProtocol.mode AND paths./cloud/mode.put.requestBody.examples.* -> set_mode, set_mode_default_FXR90, set_mode_TAG_FOCUS (all three currently say GEN2X) | getMode.md, setMode.md (if they quote the example) | YES - the 3 examples on /cloud/mode: set_mode, set_mode_default_FXR90, set_mode_TAG_FOCUS all say GEN2X -> change to GEN2 | Doc | 00:05:34 | FIXED |  | Simple |  | FIXED | All 4 examples now say GEN2 (get example + set_mode, set_mode_default_FXR90, set_mode_TAG_FOCUS). Was GEN2X.
3 | Get Mode | verbose behavior is not documented. | Document the verbose flag. Empty payload and verbose:false behave the same and omit default values; verbose:true returns almost all values. | Mayur Bhandare | GET /cloud/mode | NOT PRESENT AT ALL. Add a 'verbose' boolean (query param or request body) to the GET /cloud/mode operation. | getMode.md - document the verbose flag | YES - 'verbose' does not exist. Add it as a query param / request body on GET /cloud/mode | Dev + Doc | 00:06:24 | NOT FIXED |  | Complex | MAYUR - what does verbose:true exclude? | NOT FIXED | No 'verbose' parameter or request body on GET /cloud/mode. BLOCKED on Mayur.
4 | Inventory protocol | Inventory protocol values are incomplete. | List all supported values: Gen2, Gen2X, Hybrid. | Manoharan Balakrishnan | GET /cloud/mode, PUT /cloud/mode | GetModeResponse.inventoryProtocol.mode.enum AND SetModeRequest.inventoryProtocol.mode.enum | - | YES - inventoryProtocol.mode.enum on GET+PUT /cloud/mode. CHECK FIRST: already [GEN2X, GEN2, HYBRID] in FXR90-rest-api.yaml | Dev | 00:07:11, 00:37:46 | FIXED |  | Simple |  | FIXED | inventoryProtocol.v1.mode.enum = [GEN2X, GEN2, HYBRID].
5 | Start | doNotPersist is incorrectly documented for RFID and BLE. | State that it applies only to RFID. Remove BLE from that description. | Mayur Bhandare | PUT /cloud/start | StartInventoryRequest.doNotPersistState.description + the 'Persistence Across Reboots' table in the operation description | startInventory.md - the 'Persistence Across Reboots' table says RFID and BLE | YES - doNotPersistState.description | Doc | 00:08:53 | FIXED |  | Simple |  | FIXED | doNotPersistState.description + 'Persistence Across Reboots' table no longer mention BLE.
6 | BLE | BLE support varies by firmware. | Mention BLE support from build 4.0.11; clarify scanType is unavailable in older builds. | Mayur Bhandare | PUT /cloud/start, PUT /cloud/stop, GET+PUT /cloud/ble-config | StartInventoryRequest.scanType.description, StopInventoryRequest.scanType.description, and the ble-config operation descriptions | startInventory.md, stopInventory.md, setBleConfig.md, getBleConfig.md | YES - scanType.description on both start and stop | Doc | 00:11:00 | NOT FIXED |  | Medium |  | NOT FIXED | '4.0.11' appears nowhere in the spec. No firmware-version note on scanType.
7 | Examples - global | Examples contain options copied from FXR60 / FX9500 / FX9600. | Replace with FXR90-specific examples. | Mayur Bhandare | (global - worst in /cloud/config and /cloud/cloudConfig) | All requestBody.examples blocks | - | YES - all requestBody.examples blocks, worst in /cloud/config and /cloud/cloudConfig | Doc | 00:12:55 | NOT FIXED |  | Complex |  | NOT FIXED | FX9600 / FXR60 / FX7500 / ATR7000 still appear (mostly via GetVersionResponse.model.enum - see #16).
8 | Cloud config - WebSocket | WebSocket configuration payload is incorrect. | Replace the connection portion with the payload Mayur posted in the review comment (replace from 'additional' through the websocket block). | Mayur Bhandare | PUT /cloud/config | paths./cloud/config.put.requestBody.examples.set_config_data_websocket | setConfigMqtt.md (if it quotes the payload) | YES - example set_config_data_websocket | Doc | 00:13:37-00:15:58 | NOT FIXED |  | Medium | MAYUR - the correct WebSocket payload | NOT FIXED | set_config_data_websocket example unchanged. BLOCKED - Mayur owes the payload.
9 | Cloud config - WebSocket | WebSocket payload contains unsupported fields. | Remove GCP, verifyHost / verifyPeer, and the option transcribed as expandAll. | Mayur Bhandare | PUT /cloud/config, PUT /cloud/cloudConfig | SetConfigMqttRequest ... options.security.verifyHost and .verifyPeer (currently present); and the set_config_data_websocket example | setConfigMqtt.md, setImportCloudConfig.md | YES - options.security.verifyHost / verifyPeer + the websocket example | Dev + Doc | 00:13:48-00:14:44 | NOT FIXED |  | Medium | MAYUR - what is 'expandAll'? | NOT FIXED | options.security.verifyHost and .verifyPeer still present in SetConfigMqttRequest.
10 | Control mode | Control-mode Get Start/Stop behavior needs a note. | Document that Get Start/Stop IS supported in control mode. | Mayur Bhandare | PUT /cloud/start, PUT /cloud/stop | Operation descriptions - add a control-mode support note | startInventory.md, stopInventory.md - add a control-mode support note | NO - description text only | Doc | 00:16:02 | NOT FIXED |  | Simple |  | NOT FIXED | No control-mode note in the PUT /cloud/start or PUT /cloud/stop descriptions.
11 | Stack LED | Stack LED content is not applicable to FXR90. | Remove from FXR90 docs, or clearly label product applicability. | Mayur Bhandare | GET /cloud/stack-led, PUT /cloud/stack-led | The whole /cloud/stack-led path + GetStackledResponse, SetStackledRequest, SetStackledResponse components | getStackled.md, setStackled.md | YES - the whole /cloud/stack-led path + GetStackledResponse / SetStackledRequest / SetStackledResponse | Doc | 00:16:18 | NOT FIXED |  | Simple |  | NOT FIXED | /cloud/stack-led path still present, with GetStackledResponse / SetStackledRequest / SetStackledResponse.
12 | Cloud config | Cloud configuration contains unsupported entries. | Remove GCP and the second entry transcribed as keyboard / MQTTGC. Confirm the exact schema name. | Mayur Bhandare | PUT /cloud/cloudConfig, PUT /cloud/config | Every 'Supported values: mqtt, mqtt-GCP, mqtt-AWS, mqtt-Azure, httpPost, WEBSOCKET, tcpip-server, keyboard-emulation' description string - remove mqtt-GCP and keyboard-emulation. Also the 'Connection Types' table in the cloudConfig description. | setImportCloudConfig.md, setConfigMqtt.md - the 'Connection Types' table | YES - remove mqtt-GCP and keyboard-emulation from every connection 'type' description | Dev + Doc | 00:16:34-00:17:05 | NOT FIXED |  | Medium | MAYUR - exact name of 'keyboard' / 'MQTTGC' | NOT FIXED | mqtt-GCP x12 and keyboard-emulation x13 still in the spec.
13 | updatePassword | Description is misleading - appears to allow username changes. | Clarify that the username identifies the account and only the password is changed. MAYUR'S EXACT WORDING (00:19:08): 'This endpoint allows you to edit the admin and RFID ADM password.' | Mayur Bhandare | PUT /cloud/updatePassword | The operation description ('This endpoint allows you to configure: the username of the account to update through userName...') | updatePassword.md - rewrite to Mayur's wording | YES - the operation description on PUT /cloud/updatePassword | Doc | 00:18:46-00:19:44 | NOT FIXED |  | Simple |  | NOT FIXED | Description still reads 'the username of the account to update through userName'. Mayur's wording not applied.
14 | updatePassword | Password examples are incomplete. | Add examples for both admin and rfid-adm. | Mayur Bhandare | PUT /cloud/updatePassword | paths./cloud/updatePassword.put.requestBody.examples - only 'set_password' (admin) exists; add an rfid-adm example | - | YES - requestBody.examples on /cloud/updatePassword; only 'set_password' (admin) exists, add rfid-adm | Doc | 00:19:53 | FIXED |  | Simple |  | FIXED | Both examples present: set_password (admin) and set_password_rfidadm.
15 | Set Logs | Supported log levels are uncertain. | Verify off, fatal, trace, extra. Known supported: info, warning, debug. Update the schema after testing. | Mayur Bhandare | GET /cloud/logs, PUT /cloud/logs | logLevel.v1.components.items.level.enum - currently [OFF, FATAL, ERROR, WARNING, DEBUG, INFO, TRACE, EXTRA] | getLogs.md, setLogs.md - the 'Supported Log Levels' row | YES - logLevel.v1.components.items.level.enum | Dev | 00:21:08-00:25:46 | NOT FIXED |  | Medium | DEV - which log levels are real? | NOT FIXED | logLevel.v1 level.enum still [OFF, FATAL, ERROR, WARNING, DEBUG, INFO, TRACE, EXTRA]. BLOCKED on dev.
16 | get_version | Model schema lists other reader models. | Correct the model enum / list for FXR90. | Mayur Bhandare | GET /cloud/version | GetVersionResponse.model.enum - currently [FXR90, FX7500, FX9600, ATR7000, FXR60] | getVersion.md | YES - GetVersionResponse.model.enum. CHECK FIRST: FXR90 is already present | Dev | 00:23:55-00:24:39 | NOT FIXED |  | Simple | MAYUR - strip the other 4 models or keep? | NOT FIXED | GetVersionResponse.model.enum still [FXR90, FX7500, FX9600, ATR7000, FXR60]. Other 4 models not stripped.
17 | Server config | Server deletion limitation is undocumented. | State that the server configuration cannot be deleted using the API. | Mayur Bhandare | CONFIRM WHICH: PUT /cloud/ntpServer or PUT /cloud/config (endpoint connections) | Operation description | CONFIRM WHICH: updateNtpServer.md or setConfigMqtt.md | NO - description text only | Doc | 00:25:56 | NOT FIXED |  | Simple | MAYUR - which 'server'? NTP or cloud endpoint? | NOT FIXED | No server-deletion limitation note. BLOCKED - which 'server' is still unconfirmed.
18 | Network | Network example activates uap0 and wlan0 together. | Provide separate examples; explain they cannot be active simultaneously. | Mayur Bhandare | PUT /cloud/network | paths./cloud/network.put.requestBody.examples - the uap0 / mlan0 examples | updateNetwork.md | YES - the uap0 / mlan0 requestBody examples on PUT /cloud/network | Doc | 00:27:08-00:27:52 | FIXED |  | Medium |  | FIXED | uap0 and mlan0 have separate examples; no example activates both at once.
19 | App LED | App LED incorrectly includes blue. | Remove blue from App LED values. Blue relates only to the stack-light feature. | Mayur Bhandare | PUT /cloud/app-led | SetAppledRequest.color.enum - currently [red, amber, green, blue, off]. REMOVE 'blue'. Also the 'Supported Colors' row in the operation description. NOTE: SetStackledRequest.color KEEPS blue. | setAppLed.md - the 'Supported Colors' row | YES - SetAppledRequest.color.enum: delete 'blue'. KEEP blue in SetStackledRequest | Dev + Doc | 00:28:23-00:28:58 | FIXED |  | Simple |  | FIXED | SetAppledRequest.color.enum = [red, amber, green, off] - blue removed. SetStackledRequest correctly KEEPS blue.
20 | Stack light schema | Shared stack-light schema relates to FXR60. | Remove from FXR90 docs, or add an explicit FXR60-only note. | Mayur Bhandare | GET /cloud/stack-led, PUT /cloud/stack-led | Same components as #11 - handle together | getStackled.md, setStackled.md (same as #11) | YES - same components as #11, do them together | Dev + Doc | 00:29:01-00:29:37 | NOT FIXED |  | Simple |  | NOT FIXED | Same as #11 - stack-led still in the FXR90 spec.
21 | get_version | availableOSUpgrades and revertBackFirmware always return empty. | Known defect with an existing ticket. Document the current behavior until fixed. | Mayur Bhandare | GET /cloud/version | GetVersionResponse.availableOsUpgrades.description and .revertBackFirmware.description - add a note that these are currently always empty | getVersion.md | YES - availableOsUpgrades.description + revertBackFirmware.description: note they are always empty | Doc | 00:30:12-00:31:43 | NOT FIXED |  | Simple |  | NOT FIXED | availableOsUpgrades / revertBackFirmware descriptions carry no 'currently always empty' note.
22 | Reader Stats | Reader Stats uses DC for the power source. | Rename / map DC to Power Brick. | Mayur Bhandare | GET /cloud/status, GET /cloud/readerCapabilities | GetStatusResponse.powerSource - currently a free-text string with NO enum, so add one. Also GetReadercapabilitiesResponse.capabilities.supportedPowerSource.items.enum, currently [DC, POE, POE+, POWERBRICK, BATTERY] - both DC and POWERBRICK are listed. | getStatus.md, getReadercapabilities.md | YES - GetStatusResponse.powerSource has NO enum (add one). capabilities.supportedPowerSource.enum lists both DC and POWERBRICK | Dev | 00:34:28 | NOT FIXED |  | Medium | DEV - correct powerSource values | NOT FIXED | GetStatusResponse.powerSource still a free-text string with NO enum. capabilities.supportedPowerSource still lists BOTH DC and POWERBRICK.
23 | Reader Stats | Power-negotiation values are incomplete or incorrect. | Include / correct the disabled and success values. Confirm exact enum spelling. | Mayur Bhandare | GET /cloud/status | GetStatusResponse.powerNegotiation - currently a free-text string with NO enum. Add one. | getStatus.md | YES - GetStatusResponse.powerNegotiation has NO enum. Add one | Dev | 00:34:40 | NOT FIXED |  | Medium | DEV - exact powerNegotiation enum spelling | NOT FIXED | GetStatusResponse.powerNegotiation still a free-text string with NO enum. BLOCKED on dev for exact values.
24 | Network | Network config docs omit many FXR90 parameters. | Add all supported network configuration fields. | Mayur Bhandare | GET /cloud/network, PUT /cloud/network | GetNetworkResponse and UpdateNetworkRequest | getNetwork.md, updateNetwork.md | YES - GetNetworkResponse + UpdateNetworkRequest | Dev + Doc | 00:36:18 | PARTIAL |  | Complex |  | PARTIAL | GetNetworkResponse / UpdateNetworkRequest now cover eth0, mlan0, bnep0, wan0, uap0 with IPv4/IPv6, 802.1X, WPA2/WPA3, psim/esim, hotspot. Looks broad - needs a field-by-field sign-off against the supported list.
25 | Docs vs schema | Documentation and schemas are not synchronized. | Update both sources together; ensure Swagger reflects the schema. | Mayur Bhandare | (global) | Whole file + operation_descriptions/ | ALL 70 .md files | YES - whole file. This is the umbrella sync item | Dev + Doc | 00:36:48-00:37:09 | NOT FIXED |  | Complex |  | NOT FIXED | Umbrella item. Open until the rest are closed.
26 | tagMetadata | tagMetadata is missing readerLocation. | Add reader location, including latitude / longitude. | Mayur Bhandare | GET /cloud/mode, PUT /cloud/mode | GetModeResponse.tagMetaData.items.enum AND SetModeRequest.tagMetaData.items.enum - currently [RSSI, PHASE, SEEN_COUNT, ANTENNA, CHANNEL, PC, XPC, CRC, EPC, TID, USER, MAC, HOSTNAME]. Add READER_LOCATION (confirm exact name). | getMode.md, setMode.md | YES - tagMetaData.items.enum on GET+PUT /cloud/mode. Add READER_LOCATION (confirm exact name) | Dev | 00:39:18-00:41:54 | NOT FIXED |  | Medium | DEV - exact readerLocation name + lat/long structure | NOT FIXED | READER_LOCATION is NOT in the tagMetaData enum. Dev added a readerLocationMode.v1 schema but never wired it to anything, so the build now prunes it as unreachable.
27 | Operating Mode | Operating Mode schema is incomplete. | Add the missing modeSpecificSettings section to Get Mode and Set Mode. | Mayur Bhandare | GET /cloud/mode, PUT /cloud/mode | GetModeResponse and SetModeRequest - modeSpecificSettings is ABSENT from both (it only appears in the set_mode_TAG_FOCUS example). | getMode.md, setMode.md | YES - modeSpecificSettings is ABSENT from GetModeResponse and SetModeRequest properties (appears only in the set_mode_TAG_FOCUS example) | Dev | 00:45:27-00:53:52 | FIXED |  | Complex |  | FIXED | modeSpecificSettings IS a property of operatingMode.v1 (oneOf inventorysettings.v1 / portalsettings.v1). Reaches both GET and PUT /cloud/mode.
28 | Operating Mode | Operating Mode is missing supported fields. | Add the antenna/filter field, selects, accesses, radio start, radio stop, RSSI filter, reader location. | Mayur Bhandare | GET /cloud/mode, PUT /cloud/mode | GetModeResponse and SetModeRequest - ALL of these are absent from properties: selects, accesses, radioStartConditions, radioStopConditions, rssiFilter, readerLocation, antenna filter. (selects / radioStartConditions / radioStopConditions appear ONLY in examples.) | getMode.md, setMode.md | YES - ALL absent from properties: selects, accesses, radioStartConditions, radioStopConditions, rssiFilter, readerLocation, antenna filter | Dev | 00:54:06-00:56:35 | FIXED |  | Complex |  | FIXED | ALL now real properties of operatingMode.v1: selects, accesses, radioStartConditions, radioStopConditions, rssiFilter, filter. Previously example-only.
29 | Operating Mode | Antenna stop and radio stop are being confused. | Document as separate settings. Radio start/stop must NOT be replaced with antenna start/stop. | Mayur Bhandare | GET /cloud/mode, PUT /cloud/mode | antennaStopCondition (exists) vs radioStartConditions / radioStopConditions (missing - see #28). Keep them distinct. | getMode.md, setMode.md | YES - keep antennaStopCondition (exists) separate from radioStartConditions / radioStopConditions (missing) | Dev + Doc | 00:55:38-00:56:03 | FIXED |  | Complex |  | FIXED | antennaStopCondition and radioStartConditions / radioStopConditions coexist as separate properties. Not conflated.
30 | Operating Mode | Some fields already exist - do not duplicate. | Do NOT duplicate transmitPower, antennaStopCondition, query, delay, reportFilter. The missing filter is the RSSI / antenna filter. | Mayur Bhandare | GET /cloud/mode, PUT /cloud/mode | CONFIRMED PRESENT in both: transmitPower, antennaStopCondition, query, delayBetweenAntennaCycles, reportFilter. Leave them alone. | getMode.md, setMode.md - guardrail, no schema edit | NO - DO NOT TOUCH. transmitPower, antennaStopCondition, query, delayBetweenAntennaCycles, reportFilter already exist | Doc | 00:54:32-00:56:28 | N/A |  | Simple |  | N/A | Guardrail, no edit required. Confirmed all 5 still present: transmitPower, antennaStopCondition, query, delayBetweenAntennaCycles, reportFilter.
31 | Operating Mode | Unsupported Operating Mode values remain. | Remove beams, directionality and other unsupported values. Verify dock door (ATR-specific). | Mayur Bhandare | GET /cloud/mode, PUT /cloud/mode | Check GetModeResponse.type.enum and SetModeRequest.type.enum - currently [SIMPLE, INVENTORY, PORTAL, CONVEYOR, CUSTOM]. ALSO remove the stray SetModeRequest fields 'component', 'payload', 'linkProfile'. | getMode.md, setMode.md | YES - check type.enum [SIMPLE, INVENTORY, PORTAL, CONVEYOR, CUSTOM]. Also DELETE stray SetModeRequest fields: component, payload, linkProfile | Dev | 00:42:29, 00:48:02, 01:02:00 | PARTIAL |  | Complex | MAYUR - is 'dock door' ATR-only? | PARTIAL | DONE: directionality.v1 deleted; type.enum = [SIMPLE, INVENTORY, PORTAL, CONVEYOR, CUSTOM]. NOT DONE: stray component / payload / linkProfile still in SetModeRequest allOf, labelled 'legacy fields accepted by set_mode'.
32 | Config | XML is included although FXR90 does not support it. | Remove XML everywhere in the FXR90 documentation. | Mayur Bhandare | GET /cloud/config, PUT /cloud/config, PUT /cloud/cloudConfig | GetConfigResponse.xml (PRESENT - remove) and SetConfigMqttRequest.xml (PRESENT - remove). Also the description text 'Push a complete or partial reader XML configuration'. | getConfig.md, setConfigMqtt.md, setImportCloudConfig.md | YES - GetConfigResponse.xml and SetConfigMqttRequest.xml both PRESENT. Delete both | Dev + Doc | 00:56:46-01:00:36 | NOT FIXED |  | Simple |  | NOT FIXED | GetConfigResponse.xml and SetConfigMqttRequest.xml both still present.
33 | Endpoint connectors | Endpoint connector list is incomplete. | Add AWS and Azure to the supported endpoint connections. | Mayur Bhandare | PUT /cloud/config, PUT /cloud/cloudConfig, GET /cloud/readerCapabilities | The connection 'type' description strings, and capabilities.endpointTypesSupported | setConfigMqtt.md, setImportCloudConfig.md, getReadercapabilities.md | YES - connection 'type' descriptions + capabilities.endpointTypesSupported | Dev | 00:59:21-01:00:48 | FIXED |  | Medium |  | FIXED | mqtt-AWS and mqtt-Azure are documented connection types; AWS_IOT_CORE and AZURE_IOT_HUB appear in capabilities.endpointTypesSupported.
34 | Cloud Config | Cloud Config still contains a GCP handler. | Remove the GCP handler. | Mayur Bhandare | PUT /cloud/cloudConfig | SetImportcloudconfigRequest - all 'mqtt-GCP' references, plus the keyAlgorithm 'JWT signing algorithm for GCP connections' descriptions and the Connection Types table. | setImportCloudConfig.md | YES - all mqtt-GCP refs in SetImportcloudconfigRequest + the keyAlgorithm 'GCP connections' descriptions | Dev | 01:00:56 | NOT FIXED |  | Medium |  | NOT FIXED | Same as #12 - mqtt-GCP still throughout SetImportcloudconfigRequest, incl. the keyAlgorithm 'GCP connections' descriptions.
35 | Error codes | Error-code schema / documentation is missing. | Add it to the planned FXR90 command / error-code document. | Mayur Bhandare | (global - new) | New error-code schema. error_codes.json already exists at repo root - wire it in. | (new file needed) | YES - new error-code schema. error_codes.json exists at repo root - wire it in | Dev | 01:01:09 | NOT FIXED |  | Complex |  | NOT FIXED | No error-code schema in components. error_codes.json still unwired.
36 | Config schema | Config schema is incomplete and includes unsupported parameters. | Add every supported FXR90 parameter; remove all unsupported ones. | Mayur Bhandare | GET /cloud/config, PUT /cloud/config | GetConfigResponse and SetConfigMqttRequest - the umbrella item covering #32, #33, #34. | getConfig.md, setConfigMqtt.md | YES - GetConfigResponse + SetConfigMqttRequest. Umbrella item covering #32, #33, #34 | Dev | 01:01:43-01:02:05 | NOT FIXED |  | Complex |  | NOT FIXED | Umbrella over #32/#33/#34. Open while XML and GCP remain.

## 2. To Verify
OPEN / UNRESOLVED - confirm before treating as defects
# | Item | Blocks issue | Who confirms | Answer | Status
1 | Pre-selection in control mode - UNRESOLVED. Said not to be part of control, but the live request returned success. Reviewer said to leave it. | - | Mayur |  | Open
2 | What exactly does verbose:true EXCLUDE on Get Mode? 'I need to check that, what are the things will not come.' | #3 | Mayur |  | Open - Mayur owes this
3 | Which log levels are actually supported - off, fatal, trace, extra? | #15 | Dev |  | Open
4 | Verify readerLocation against the implementation, and its exact enum name. | #26, #28 | Dev |  | Open
5 | Confirm dock door / ATR applicability. | #31 | Dev |  | Open
6 | Exact schema name of the unsupported cloud entry transcribed as 'keyboard' / 'MQTTGC'. | #12, #34 | Mayur |  | Open
7 | Exact power-negotiation enum spelling ('disabled', 'success'). | #23 | Dev |  | Open
8 | The option transcribed as 'expandAll'. | #9 | Mayur |  | Open
9 | Which 'server' cannot be deleted - NTP server, or a cloud endpoint connection? | #17 | Mayur |  | Open
10 | Should the model enum keep FX7500 / FX9600 / ATR7000 / FXR60, or be stripped to FXR90 only? | #16 | Mayur |  | Open

## 3. Work Plan
WORK PLAN BY COMPLEXITY - do them in this order
Tier | # | Item | Why it is this tier | Blocked on
Simple | 19 | App LED: remove blue | Delete 'blue' from SetAppledRequest.color.enum. One word. KEEP blue in SetStackledRequest.
Simple | 2 | Get/Set Mode example: Gen2X -> Gen2 | Three examples say GEN2X. Find and replace. HIGHEST CUSTOMER IMPACT ON THE LIST - this is the one that generates SPRs.
Simple | 4 | inventoryProtocol enum | ALREADY DONE - enum is already [GEN2X, GEN2, HYBRID]. Verify and close.
Simple | 16 | Model enum | FXR90 is ALREADY present. Only decision: strip the other 4 models or keep them. | MAYUR
Simple | 32 | Remove XML | GetConfigResponse.xml and SetConfigMqttRequest.xml - delete two properties.
Simple | 31 | Delete stray mode fields | PART A ONLY: delete component, payload, linkProfile from SetModeRequest. Part B (beams / dock door) is Complex - see below.
Simple | 13 | Password description | Mayur gave the exact replacement sentence at 00:19:08. Paste it.
Simple | 14 | Password examples | Add an rfid-adm example beside the existing admin one.
Simple | 5 | doNotPersist: remove BLE | Remove BLE from the description and the persistence table.
Simple | 10 | Control-mode note | Add one sentence: Get Start/Stop IS supported in control mode.
Simple | 21 | getVersion empty fields | Add 'currently always returns empty' to two field descriptions.
Simple | 11+20 | Remove Stack LED | Delete the /cloud/stack-led path and its 3 components. One fix closes two issues.
Simple | 30 | Do-not-duplicate guardrail | NO EDIT AT ALL. This is a warning for items 27-31.
Simple | 1 | Fix broken links | Simple IF the count is small. Audit first.
Simple | 17 | Server-delete limitation | One sentence - once you know which 'server' is meant. | MAYUR
Medium | 12+34 | Remove GCP + keyboard-emulation | Strings are scattered across EVERY connection-type description in the file. Tedious, not hard. Do both together. | MAYUR - exact name of MQTTGC
Medium | 9 | WebSocket: remove unsupported fields | Remove verifyHost / verifyPeer. Blocked only on what 'expandAll' actually is. | MAYUR
Medium | 8 | WebSocket payload | Easy once Mayur sends the payload he referenced in the comment. | MAYUR
Medium | 6 | BLE version notes | Touches 4 .md files. Mechanical.
Medium | 18 | Split uap0 / mlan0 examples | Separate the examples and add the mutual-exclusion note.
Medium | 33 | Add AWS + Azure connectors | Update the connector list and capabilities.endpointTypesSupported.
Medium | 22 | powerSource: DC -> Power Brick | powerSource has NO enum today. Adding one is easy - you need the correct values. | DEV
Medium | 23 | powerNegotiation values | powerNegotiation has NO enum today. Same as above. | DEV - exact spelling
Medium | 15 | Log levels | Trivial edit. Blocked on which of off / fatal / trace / extra are real. | DEV
Medium | 26 | tagMetaData: add readerLocation | Add READER_LOCATION to the enum - need the exact name and lat/long structure. | DEV
Complex | 27+28+29 | OPERATING MODE - THE BIG ONE | modeSpecificSettings, selects, accesses, radioStartConditions, radioStopConditions, rssiFilter, readerLocation are ALL absent from properties - several exist only inside examples. Deeply nested objects to author from scratch, on BOTH Get and Set. Plus keep antennaStopCondition distinct from radioStopConditions. Treat as one project, not three tickets. THIS IS MOST OF THE REAL EFFORT.
Complex | 36 | Config schema completeness | 'Include every supported parameter, remove every unsupported one' - unbounded until someone defines the supported set. Swallows 32, 33, 34.
Complex | 24 | Network schema completeness | Same shape as 36, for the network schema.
Complex | 3 | verbose flag | Does not exist in the spec AND nobody knows what verbose:true excludes. HARD BLOCKED. | MAYUR
Complex | 35 | Error-code schema | New schema. error_codes.json exists at repo root but is not wired in.
Complex | 25 | Docs / schema sync | The umbrella item - effectively 'do all the others'.
Complex | 7 | Replace stale examples | Scope unknown until every example block is audited.
Complex | 31 | Remove beams / directionality / dock door | PART B: removing beams and directionality is easy. Confirming dock door / ATR is not, and it is unresolved. | MAYUR

## 4. Verification
VERIFICATION RUN - 14 Jul 2026, against RestAPI/FXR90-rest-api.yaml
Source: RestDeveloperfile.yaml (developer's openAPISpecnew.yaml) -> built by RestAPI/scripts/build_fxr90_rest_api.py
# | Verdict | Evidence in the generated spec
1 | NOT FIXED | info.description + externalDocs.url unchanged. No link audit done.
2 | FIXED | All 4 examples now say GEN2 (get example + set_mode, set_mode_default_FXR90, set_mode_TAG_FOCUS). Was GEN2X.
3 | NOT FIXED | No 'verbose' parameter or request body on GET /cloud/mode. BLOCKED on Mayur.
4 | FIXED | inventoryProtocol.v1.mode.enum = [GEN2X, GEN2, HYBRID].
5 | FIXED | doNotPersistState.description + 'Persistence Across Reboots' table no longer mention BLE.
6 | NOT FIXED | '4.0.11' appears nowhere in the spec. No firmware-version note on scanType.
7 | NOT FIXED | FX9600 / FXR60 / FX7500 / ATR7000 still appear (mostly via GetVersionResponse.model.enum - see #16).
8 | NOT FIXED | set_config_data_websocket example unchanged. BLOCKED - Mayur owes the payload.
9 | NOT FIXED | options.security.verifyHost and .verifyPeer still present in SetConfigMqttRequest.
10 | NOT FIXED | No control-mode note in the PUT /cloud/start or PUT /cloud/stop descriptions.
11 | NOT FIXED | /cloud/stack-led path still present, with GetStackledResponse / SetStackledRequest / SetStackledResponse.
12 | NOT FIXED | mqtt-GCP x12 and keyboard-emulation x13 still in the spec.
13 | NOT FIXED | Description still reads 'the username of the account to update through userName'. Mayur's wording not applied.
14 | FIXED | Both examples present: set_password (admin) and set_password_rfidadm.
15 | NOT FIXED | logLevel.v1 level.enum still [OFF, FATAL, ERROR, WARNING, DEBUG, INFO, TRACE, EXTRA]. BLOCKED on dev.
16 | NOT FIXED | GetVersionResponse.model.enum still [FXR90, FX7500, FX9600, ATR7000, FXR60]. Other 4 models not stripped.
17 | NOT FIXED | No server-deletion limitation note. BLOCKED - which 'server' is still unconfirmed.
18 | FIXED | uap0 and mlan0 have separate examples; no example activates both at once.
19 | FIXED | SetAppledRequest.color.enum = [red, amber, green, off] - blue removed. SetStackledRequest correctly KEEPS blue.
20 | NOT FIXED | Same as #11 - stack-led still in the FXR90 spec.
21 | NOT FIXED | availableOsUpgrades / revertBackFirmware descriptions carry no 'currently always empty' note.
22 | NOT FIXED | GetStatusResponse.powerSource still a free-text string with NO enum. capabilities.supportedPowerSource still lists BOTH DC and POWERBRICK.
23 | NOT FIXED | GetStatusResponse.powerNegotiation still a free-text string with NO enum. BLOCKED on dev for exact values.
24 | PARTIAL | GetNetworkResponse / UpdateNetworkRequest now cover eth0, mlan0, bnep0, wan0, uap0 with IPv4/IPv6, 802.1X, WPA2/WPA3, psim/esim, hotspot. Looks broad - needs a field-by-field sign-off against the supported list.
25 | NOT FIXED | Umbrella item. Open until the rest are closed.
26 | NOT FIXED | READER_LOCATION is NOT in the tagMetaData enum. Dev added a readerLocationMode.v1 schema but never wired it to anything, so the build now prunes it as unreachable.
27 | FIXED | modeSpecificSettings IS a property of operatingMode.v1 (oneOf inventorysettings.v1 / portalsettings.v1). Reaches both GET and PUT /cloud/mode.
28 | FIXED | ALL now real properties of operatingMode.v1: selects, accesses, radioStartConditions, radioStopConditions, rssiFilter, filter. Previously example-only.
29 | FIXED | antennaStopCondition and radioStartConditions / radioStopConditions coexist as separate properties. Not conflated.
30 | N/A | Guardrail, no edit required. Confirmed all 5 still present: transmitPower, antennaStopCondition, query, delayBetweenAntennaCycles, reportFilter.
31 | PARTIAL | DONE: directionality.v1 deleted; type.enum = [SIMPLE, INVENTORY, PORTAL, CONVEYOR, CUSTOM]. NOT DONE: stray component / payload / linkProfile still in SetModeRequest allOf, labelled 'legacy fields accepted by set_mode'.
32 | NOT FIXED | GetConfigResponse.xml and SetConfigMqttRequest.xml both still present.
33 | FIXED | mqtt-AWS and mqtt-Azure are documented connection types; AWS_IOT_CORE and AZURE_IOT_HUB appear in capabilities.endpointTypesSupported.
34 | NOT FIXED | Same as #12 - mqtt-GCP still throughout SetImportcloudconfigRequest, incl. the keyAlgorithm 'GCP connections' descriptions.
35 | NOT FIXED | No error-code schema in components. error_codes.json still unwired.
36 | NOT FIXED | Umbrella over #32/#33/#34. Open while XML and GCP remain.