## READ ME
FXR90 — Fix Backlog
Generated 2026-07-08 from the schema/description audits. One row = one actionable item.
How to use:
1. Work the 'Backlog' sheet top-down: P1 items first (they affect correctness or block tooling).
2. Update the Status column as you go (dropdown: Open / In Progress / Done / Won't Fix).
3. The 'Missing Descriptions' sheet is the detailed worklist for backlog item D-06 — one row per undocumented response field.
4. Rows marked EVENT are off-limits until the events owner approves (per project rule: no event changes).
Priorities:
P1 = correctness bug or blocks integrators/tooling. P2 = real gap, plan into normal work. P3 = cosmetic/consistency.
Already fixed (for reference, no action):
- Command/response id enums locked (5 ops) · get_CACertificates removed · MQTT aligned to REST (18 enum + 23 type + 481 desc)
- eventsConfig dedup bug fixed in build_openapi.py + REST spec rebuilt · 21 REST + 33 MQTT operation-description fixes · openapi_md.json regenerated

## Backlog
ID | Priority | Area | Issue | Location / Files | Evidence & Detail | Recommended Fix | Effort | Status
D-01 | P1 | Docs — errors | Error codes are not documented anywhere in the API reference | error_codes.json · scripts/generate_openapi_tags_md.py · operation_descriptions/*.md | error_codes.json holds per-code cause + recommended_action mapped to commands, but the generated doc has 0 references to it. Every operation only shows a generic failure {code, message}. Generator already defines a 'Response codes:' marker that nothing uses. | Extend the generator to inject a per-command response-codes table from error_codes.json (filter by the 'commands' field). Alternatively add a 'Response codes:' section per md file. | M | Open
D-02 | P1 | Docs — onboarding | No MQTT quickstart: topics, auth, QoS, correlation not documented | info_description.md (feeds docs/openapi_md.json info.description) | Landing description is 216 chars. Missing: which topic commands are published to, which topic responses/events arrive on, authentication, QoS guidance, command_id correlation, and an explanation that 'POST /get_version' is an OpenAPI rendering convention (this is MQTT, not HTTP). | Write a proper intro in info_description.md covering topic structure, auth, QoS, command_id request/response correlation, and the rendering convention. Regenerate openapi_md.json. | M | Open
S-01 | P1 | Schema — OAS3 validity | set_config batching uses type:['object','null'] / type:'null' — illegal in OpenAPI 3.0 | schemas/references/request_payload/readerConfig.yaml (~line 2443) · importCloudConfigReq.yaml (check same pattern) | Generator's validation fails on paths./set_config.post.requestBody (…additionalOptions.batching.oneOf[0].type = 'null'). Strict validators and code generators will reject the doc. Pre-existing (already in HEAD). | Replace JSON-Schema style null typing with OAS 3.0 'nullable: true' (drop the type:'null' oneOf branch, put nullable:true on the object). Regenerate openapi_md.json. | S | Open
S-02 | P1 | REST — schema vs example | 6 REST examples contradict their schemas | openAPISpec2.yaml (source) → rebuild RestAPI/FXR90-rest-api.yaml | PUT /cloud/mode: transmitPower schema=array, example=31.5. GET+PUT /cloud/network (4 examples): IPV6 prefix schema=string, examples=integer 64. GET /cloud/config: userDefined schema=object, example=null. Detail in RestAPI/schema_example_report.xlsx. | Decide direction per field (prefix is almost certainly integer; transmitPower example should be [31.5]; userDefined needs nullable or a real example), fix in openAPISpec2.yaml, rebuild. | S | Open
S-03 | P1 | Build — derived artifacts stale | Expanded schemas and bundle exports not regenerated after modular fixes | schemas/commands_expanded/ · schemas/response_expanded/ · 'Command Schemas.json' · 'Response Schemas.json' | The _expanded copies still carry pre-alignment enums/types/descriptions; the two bundle JSONs still contain the removed get_CACertificates (3 component blocks + tag entries). No generator script found in repo for these. | Locate/write the bundler that produces them from the modular source and regenerate; or deprecate the derived copies if nothing consumes them. | M | Open
D-06 | P2 | Docs — response depth | 303 response properties across 67 operations have no description | schemas/references/response_payload/*.yaml · schemas/response/** | 21% of response properties undocumented vs only 6% on requests. Worst: get_network (49), get_readerCapabilities (37), get_bleConfig (18), get_status (17). Full worklist on the 'Missing Descriptions' sheet. | Work through the 'Missing Descriptions' sheet; start with the top 4 operations (121 of 303). Skip rows flagged EVENT. | L | Open
D-07 | P2 | Docs — template | 'Rules and Constraints' section missing from all SET/modifying commands | operation_descriptions/set_*.md and other modifying commands (~35 files) | The agreed SET-command template has 4 sections (Description, Command Details, Before You Begin, Rules and Constraints). Current docs consistently use only 3. 0 of 70 commands have a Rules section. | Decide which is authoritative. If the template: add Rules and Constraints to ~35 modifying commands. If the docs: update the template definition. | L | Open
R-01 | P2 | REST — modeling gaps | REST omits schema detail that the MQTT side documents | openAPISpec2.yaml → rebuild | 1) GPIO-LED conditions: {operator, operands[]} variant missing in REST (1 shared schema, surfaces in 20 paths). 2) additionalOptions.batching missing type:object (2 places). 3) GET /cloud/mode has no 'verbose' param but MQTT get_mode supports it. | Add the conditions oneOf variant and batching type in the REST source; decide whether verbose should be exposed as a REST query param or documented as MQTT-only. | M | Open
R-02 | P2 | REST — missing enums | MQTT is stricter than REST on 2 readerCapabilities fields | openAPISpec2.yaml → rebuild | capabilities.endpointTypesSupported[].type and capabilities.apiSupported.versions[].version have enums on the MQTT side but are free strings in REST. | Copy the MQTT enums into the REST source (do NOT remove them from MQTT). | S | Open
R-03 | P2 | Design decision | /cloud/mode and /cloud/config shapes diverge structurally between REST and MQTT | operatingMode / readerConfig schemas on both sides | MQTT models several fields as oneOf (object OR array: antennaStopCondition, query, transmitPower, accesses); REST picks a single shape. ~13 type diffs + most of the 476 single-side field paths trace to this. | API owner decision: pick the canonical shape per field, then align the other side. Not a mechanical fix. | L | Open
D-11 | P3 | Docs — naming | Operation summaries inconsistent with Get/Set convention | operation_descriptions/refresh-cert.md · revertback.md (summaries come from schema titles/tag_config) | Summaries mostly 'Get X'/'Set X' but 'Refresh-Cert' and 'Revertback' leak raw command names into the rendered nav. | Normalize display summaries: 'Refresh Certificate', 'Revert Firmware'. Command names themselves must NOT change (breaking). | S | Open
D-12 | P3 | Docs — naming | Command naming mixes snake_case, camelCase, kebab-case | schemas/commands/** (get_appled, set_dataToRG, refresh-cert, uninstall-user-app) | Cosmetic inconsistency visible throughout the doc. Renaming commands would break existing integrations. | Do not rename. Document the inconsistency as known in the intro, and enforce a convention for NEW commands only. | S | Open
E-01 | P3 | Events (needs owner approval) | 13 event messages ship without examples; some event payload fields undescribed | schemas/events/ · schemas/tag-events/ · operation_descriptions/<event>.md | EVENT — off-limits per project rule. Noted for the events owner: no x-examples on any of the 13 event bodies; async-events/heartbeat have ~11 undescribed fields. | Hand to events owner; do not edit without approval. | M | Open
S-04 | P3 | Schema — file naming | get_supportedStandardList files have inconsistent casing | schemas/commands/region/get_supportedStandardList.json vs schemas/response/region/get_SupportedStandardlist_response.json | Command and response enums match; only the file names differ in case. Harmless but trips up tooling that pairs files by name. | Rename the response file to match the command file's casing (verify nothing references the old name). | S | Open

## Missing Descriptions
Operation | Field path (no description) | Event? | Status
get_network | response |  | Open
get_network | payload |  | Open
get_network | payload.hostName |  | Open
get_network | payload.networkInterface.eth0.IPV4 |  | Open
get_network | payload.networkInterface.eth0.IPV6 |  | Open
get_network | payload.networkInterface.mlan0.IPV4 |  | Open
get_network | payload.networkInterface.mlan0.IPV6 |  | Open
get_network | payload.networkInterface.wan0.psim.preferredNetworkType |  | Open
get_network | payload.networkInterface.wan0.psim.enableIPv6 |  | Open
get_network | payload.networkInterface.wan0.psim.enablePin |  | Open
get_network | payload.networkInterface.wan0.psim.enableRoaming |  | Open
get_network | payload.networkInterface.wan0.psim.currentDataClass |  | Open
get_network | payload.networkInterface.wan0.psim.highestAvailableDataClass |  | Open
get_network | payload.networkInterface.wan0.psim.currentServiceProvider |  | Open
get_network | payload.networkInterface.wan0.psim.registerState |  | Open
get_network | payload.networkInterface.wan0.psim.packetServiceState |  | Open
get_network | payload.networkInterface.wan0.psim.internetAccess |  | Open
get_network | payload.networkInterface.wan0.psim.simState |  | Open
get_network | payload.networkInterface.wan0.psim.signalBar |  | Open
get_network | payload.networkInterface.wan0.psim.rssi |  | Open
get_network | payload.networkInterface.wan0.psim.rsrp |  | Open
get_network | payload.networkInterface.wan0.psim.rsrq |  | Open
get_network | payload.networkInterface.wan0.psim.snr |  | Open
get_network | payload.networkInterface.wan0.esim.apn |  | Open
get_network | payload.networkInterface.wan0.esim.preferredNetworkType |  | Open
get_network | payload.networkInterface.wan0.esim.enableIPv6 |  | Open
get_network | payload.networkInterface.wan0.esim.enablePin |  | Open
get_network | payload.networkInterface.wan0.esim.enableRoaming |  | Open
get_network | payload.networkInterface.wan0.esim.currentDataClass |  | Open
get_network | payload.networkInterface.wan0.esim.highestAvailableDataClass |  | Open
get_network | payload.networkInterface.wan0.esim.currentServiceProvider |  | Open
get_network | payload.networkInterface.wan0.esim.registerState |  | Open
get_network | payload.networkInterface.wan0.esim.packetServiceState |  | Open
get_network | payload.networkInterface.wan0.esim.internetAccess |  | Open
get_network | payload.networkInterface.wan0.esim.simState |  | Open
get_network | payload.networkInterface.wan0.esim.signalBar |  | Open
get_network | payload.networkInterface.wan0.esim.rssi |  | Open
get_network | payload.networkInterface.wan0.esim.rsrp |  | Open
get_network | payload.networkInterface.wan0.esim.rsrq |  | Open
get_network | payload.networkInterface.wan0.esim.snr |  | Open
get_network | payload.networkInterface.wan0.Status |  | Open
get_network | payload.networkInterface.wan0.isEnabled |  | Open
get_network | payload.networkInterface.wan0.macAddress |  | Open
get_network | payload.networkInterface.uap0.Clients[].hostName |  | Open
get_network | payload.networkInterface.uap0.Clients[].IP |  | Open
get_network | payload.networkInterface.uap0.Clients[].MAC |  | Open
get_network | payload.networkInterface.uap0.Status |  | Open
get_network | payload.networkInterface.uap0.isEnabled |  | Open
get_network | payload.networkInterface.uap0.macAddress |  | Open
get_readerCapabilities | response |  | Open
get_readerCapabilities | payload |  | Open
get_readerCapabilities | payload.capabilities |  | Open
get_readerCapabilities | payload.capabilities.apiSupported |  | Open
get_readerCapabilities | payload.capabilities.apiSupported.versions |  | Open
get_readerCapabilities | payload.capabilities.apiSupported.versions[].documentation |  | Open
get_readerCapabilities | payload.capabilities.apiSupported.versions[].version |  | Open
get_readerCapabilities | payload.capabilities.appLEDColors |  | Open
get_readerCapabilities | payload.capabilities.asyncManagementEventsSupported |  | Open
get_readerCapabilities | payload.capabilities.beepersSupported |  | Open
get_readerCapabilities | payload.capabilities.clockSupport |  | Open
get_readerCapabilities | payload.capabilities.daAppPackageFormat |  | Open
get_readerCapabilities | payload.capabilities.daAppsSupported |  | Open
get_readerCapabilities | payload.capabilities.daLanguageBindings |  | Open
get_readerCapabilities | payload.capabilities.directionalitySupported |  | Open
get_readerCapabilities | payload.capabilities.endpointTypesSupported |  | Open
get_readerCapabilities | payload.capabilities.endpointTypesSupported[].SSLSupported |  | Open
get_readerCapabilities | payload.capabilities.endpointTypesSupported[].authenticationTypesSupported |  | Open
get_readerCapabilities | payload.capabilities.endpointTypesSupported[].batchingSupported |  | Open
get_readerCapabilities | payload.capabilities.endpointTypesSupported[].dataOnly |  | Open
get_readerCapabilities | payload.capabilities.endpointTypesSupported[].retentionSupported |  | Open
get_readerCapabilities | payload.capabilities.endpointTypesSupported[].type |  | Open
get_readerCapabilities | payload.capabilities.keypadSupport |  | Open
get_readerCapabilities | payload.capabilities.llrpSupported |  | Open
get_readerCapabilities | payload.capabilities.maxAppLEDs |  | Open
get_readerCapabilities | payload.capabilities.maxDataEndpoints |  | Open
get_readerCapabilities | payload.capabilities.maxNumOperationsInAccessSequence |  | Open
get_readerCapabilities | payload.capabilities.maxNumPreFilters |  | Open
get_readerCapabilities | payload.capabilities.messageFormatsSupported |  | Open
get_readerCapabilities | payload.capabilities.numGPIs |  | Open
get_readerCapabilities | payload.capabilities.numGPOs |  | Open
get_readerCapabilities | payload.capabilities.restAPISupported |  | Open
get_readerCapabilities | payload.capabilities.rssiFilterSupported |  | Open
get_readerCapabilities | payload.capabilities.supportedDisplayType |  | Open
get_readerCapabilities | payload.capabilities.supportedTagDataFormat |  | Open
get_readerCapabilities | payload.capabilities.tagLocationingSupported |  | Open
get_readerCapabilities | payload.capabilities.triggers |  | Open
get_bleConfig | response |  | Open
get_bleConfig | payload |  | Open
get_bleConfig | payload.ble |  | Open
get_bleConfig | payload.ble.enable |  | Open
get_bleConfig | payload.ble.scanIntervalSec |  | Open
get_bleConfig | payload.ble.additionalFilters |  | Open
get_bleConfig | payload.ble.additionalFilters.rssi |  | Open
get_bleConfig | payload.ble.additionalFilters.serviceUuids16 |  | Open
get_bleConfig | payload.ble.additionalFilters.serviceUuids128 |  | Open
get_bleConfig | payload.ble.protocols.iBeacon |  | Open
get_bleConfig | payload.ble.protocols.iBeacon.enabled |  | Open
get_bleConfig | payload.ble.protocols.iBeacon.filters |  | Open
get_bleConfig | payload.ble.protocols.altBeacon |  | Open
get_bleConfig | payload.ble.protocols.altBeacon.enabled |  | Open
get_bleConfig | payload.ble.protocols.altBeacon.filters |  | Open
get_bleConfig | payload.ble.protocols.eddystone |  | Open
get_bleConfig | payload.ble.protocols.eddystone.enabled |  | Open
get_bleConfig | payload.ble.protocols.generic.enabled |  | Open
get_status | response |  | Open
get_status | payload |  | Open
get_status | payload.flash.platform.free |  | Open
get_status | payload.flash.platform.total |  | Open
get_status | payload.flash.platform.used |  | Open
get_status | payload.flash.readerConfig.free |  | Open
get_status | payload.flash.readerConfig.total |  | Open
get_status | payload.flash.readerConfig.used |  | Open
get_status | payload.flash.readerData.free |  | Open
get_status | payload.flash.readerData.total |  | Open
get_status | payload.flash.readerData.used |  | Open
get_status | payload.flash.rootFileSystem.free |  | Open
get_status | payload.flash.rootFileSystem.total |  | Open
get_status | payload.flash.rootFileSystem.used |  | Open
get_status | payload.systemTime |  | Open
get_status | payload.temperature |  | Open
get_status | payload.uptime |  | Open
get_gpsCoordinates | command |  | Open
get_gpsCoordinates | command_id |  | Open
get_gpsCoordinates | response |  | Open
get_gpsCoordinates | payload |  | Open
get_gpsCoordinates | payload.lastReportedTime |  | Open
get_gpsCoordinates | payload.latitude |  | Open
get_gpsCoordinates | payload.longitude |  | Open
get_gpsCoordinates | payload.satellitesUsed |  | Open
get_eSimConfig | command |  | Open
get_eSimConfig | command_id |  | Open
get_eSimConfig | response |  | Open
get_eSimConfig | payload |  | Open
get_eSimConfig | payload.eid |  | Open
get_eSimConfig | payload.imei |  | Open
get_eSimConfig | payload.profiles |  | Open
async-events | data.reader_gateway.dataPathStatistics | EVENT — do not edit | Open
async-events | data.reader_gateway.dataPathStatistics[].noLockQDepth | EVENT — do not edit | Open
async-events | data.reader_gateway.interfaceConnectionStatus | EVENT — do not edit | Open
async-events | data.system.GPI | EVENT — do not edit | Open
async-events | data.system.GPO | EVENT — do not edit | Open
async-events | data.updateProgressDetails | EVENT — do not edit | Open
get_gpostatus | response |  | Open
get_gpostatus | payload |  | Open
get_gpostatus | payload.1 |  | Open
get_gpostatus | payload.2 |  | Open
get_gpostatus | payload.3 |  | Open
get_gpostatus | payload.4 |  | Open
get_mode | response |  | Open
get_mode | payload |  | Open
get_mode | payload.delayBetweenAntennaCycles |  | Open
get_mode | payload.query |  | Open
get_mode | payload.inventoryProtocol |  | Open
get_mode | payload.reportFilter |  | Open
heartbeat | reader_gateway.dataPathStatistics | EVENT — do not edit | Open
heartbeat | reader_gateway.dataPathStatistics[].noLockQDepth | EVENT — do not edit | Open
heartbeat | reader_gateway.interfaceConnectionStatus | EVENT — do not edit | Open
heartbeat | system.GPI | EVENT — do not edit | Open
heartbeat | system.GPO | EVENT — do not edit | Open
get_impinjGen2X | command |  | Open
get_impinjGen2X | command_id |  | Open
get_impinjGen2X | response |  | Open
get_impinjGen2X | payload |  | Open
get_logs_syslog | response |  | Open
get_logs_syslog | payload |  | Open
get_logs_syslog | payload.binary |  | Open
get_logs_syslog | payload.filename |  | Open
get_preSelection | command |  | Open
get_preSelection | command_id |  | Open
get_preSelection | response |  | Open
get_preSelection | payload |  | Open
get_radio_pkt_logs | response |  | Open
get_radio_pkt_logs | payload |  | Open
get_radio_pkt_logs | payload.binary |  | Open
get_radio_pkt_logs | payload.filename |  | Open
get_rc_log | response |  | Open
get_rc_log | payload |  | Open
get_rc_log | payload.binary |  | Open
get_rc_log | payload.filename |  | Open
get_readPoints | command |  | Open
get_readPoints | command_id |  | Open
get_readPoints | response |  | Open
get_readPoints | payload |  | Open
get_rg_error_logs | response |  | Open
get_rg_error_logs | payload |  | Open
get_rg_error_logs | payload.filename |  | Open
get_rg_error_logs | payload.binary |  | Open
get_rg_warn_logs | response |  | Open
get_rg_warn_logs | payload |  | Open
get_rg_warn_logs | payload.binary |  | Open
get_rg_warn_logs | payload.filename |  | Open
get_supportedStandardList | command_id |  | Open
get_supportedStandardList | response |  | Open
get_supportedStandardList | payload |  | Open
get_supportedStandardList | payload.SupportedStandards |  | Open
set_dataToRG | command |  | Open
set_dataToRG | command_id |  | Open
set_dataToRG | response |  | Open
set_dataToRG | payload |  | Open
set_eSimConfig | command |  | Open
set_eSimConfig | command_id |  | Open
set_eSimConfig | response |  | Open
set_eSimConfig | payload |  | Open
set_impinjGen2X | command |  | Open
set_impinjGen2X | command_id |  | Open
set_impinjGen2X | response |  | Open
set_impinjGen2X | payload |  | Open
set_passthru | command |  | Open
set_passthru | command_id |  | Open
set_passthru | response |  | Open
set_passthru | payload |  | Open
set_password | command |  | Open
set_password | command_id |  | Open
set_password | response |  | Open
set_password | payload |  | Open
set_preSelection | command |  | Open
set_preSelection | command_id |  | Open
set_preSelection | response |  | Open
set_preSelection | payload |  | Open
set_region | command |  | Open
set_region | command_id |  | Open
set_region | response |  | Open
set_region | payload |  | Open
autostart_user_app | response |  | Open
autostart_user_app | payload |  | Open
del_certs | response |  | Open
del_certs | payload |  | Open
del_radio_pkt_logs | response |  | Open
del_radio_pkt_logs | payload |  | Open
del_syslogs | response |  | Open
del_syslogs | payload |  | Open
get_SupportedRegionList | response |  | Open
get_SupportedRegionList | payload |  | Open
get_appled | response |  | Open
get_appled | payload |  | Open
get_cableLossCompensation | response |  | Open
get_cableLossCompensation | payload |  | Open
get_certs | response |  | Open
get_certs | payload |  | Open
get_config | response |  | Open
get_config | payload |  | Open
get_gpi_status | response |  | Open
get_gpi_status | payload |  | Open
get_hostname | response |  | Open
get_hostname | payload |  | Open
get_logs | response |  | Open
get_logs | payload |  | Open
get_ntpServer | response |  | Open
get_ntpServer | payload |  | Open
get_region | response |  | Open
get_region | payload |  | Open
get_timeZone | response |  | Open
get_timeZone | payload |  | Open
get_user_apps | response |  | Open
get_user_apps | payload |  | Open
install_user_app | response |  | Open
install_user_app | payload |  | Open
reboot | response |  | Open
reboot | payload |  | Open
refresh-cert | response |  | Open
refresh-cert | payload |  | Open
revertback | response |  | Open
revertback | payload |  | Open
set_appled | response |  | Open
set_appled | payload |  | Open
set_bleConfig | response |  | Open
set_bleConfig | payload |  | Open
set_cableLossCompensation | response |  | Open
set_cableLossCompensation | payload |  | Open
set_config | response |  | Open
set_config | payload |  | Open
set_gpo | response |  | Open
set_gpo | payload |  | Open
set_hostname | response |  | Open
set_hostname | payload |  | Open
set_importCloudConfig | response |  | Open
set_importCloudConfig | payload |  | Open
set_logs | response |  | Open
set_logs | payload |  | Open
set_mode | response |  | Open
set_mode | payload |  | Open
set_network | response |  | Open
set_network | payload |  | Open
set_ntpServer | response |  | Open
set_ntpServer | payload |  | Open
set_os | response |  | Open
set_os | payload |  | Open
set_req_usr_app | response |  | Open
set_req_usr_app | payload |  | Open
set_timeZone | response |  | Open
set_timeZone | payload |  | Open
set_update_cert | response |  | Open
set_update_cert | payload |  | Open
start_user_app | response |  | Open
start_user_app | payload |  | Open
stop | response |  | Open
stop | payload |  | Open
stop_user_app | response |  | Open
stop_user_app | payload |  | Open
uninstall-user-app | response |  | Open
uninstall-user-app | payload |  | Open
firmwareUpdateProgress | updateProgressDetails | EVENT — do not edit | Open
start | payload |  | Open