## 0. Summary
FXR90 REST API - Developer Working Session
Prepared for | Sit-down with the developer to close out the open REST API issues
Date | 13 July 2026
Schema source of truth | RestDeveloperfile.yaml (50 paths, 58 operations that have an operationId)
Description source | RestAPI/operation_descriptions/ (70 .md files)
Prior tracker | RestAPI/developer_feedback/endpoint_issues.xlsx
WHAT CHANGED SINCE THE LAST TRACKER
Good news | The 3 'Not Fixed / REGRESSION' items (missing GET and PUT /cloud/logs, and updatePassword carrying the logs request body) DO NOT exist in RestDeveloperfile.yaml. Those were defects in openAPISpec2.yaml only. Against the developer file they are already correct.
Also already fixed | impinjTagQuieting.v1 now has a proper 'type'. set_updateCertificate 'required' is now correctly [url, type, name].
New findings | 12 operations have NO operationId at all. A further 19 have operationId casing that does not match the description files.
OPEN WORK
Schema issues | 17 (tab 1)
OperationId issues | 31 = 12 missing + 19 casing (tab 2)
Description issues | 6 (tab 3)
Decisions needed from dev | 9 (tab 4)
NEXT ACTION (agreed with Mayur on the call)
Gating item | Update the NTP server description FIRST as a single sample, get Mayur's review, and only then roll the template out to the remaining commands.
HOW TO USE THIS SHEET
In the meeting | Work top-down through tab 4 (Decisions Needed). Each answer unblocks rows in tabs 1 to 3.
Owner column | Dev = a code or schema change on their side. Doc = I fix it in the spec and descriptions.
Fill in | The 'Decision' and 'Dev Notes / Agreed Action' columns during the discussion.

## 1. Schema Issues
SCHEMA ISSUES - verified against RestDeveloperfile.yaml (13 Jul 2026)
SL | Endpoint | Method | operationId | MQTT Command | Issue (verified in RestDeveloperfile.yaml) | Evidence / What the file says today | Proposed Fix | Owner | Priority | Decision Needed From Dev? | Status | Dev Notes / Agreed Action
1 | /cloud/hostName | GET + PUT | getHostName / setHostName | get_hostname / set_hostName | Field casing mismatch between GET and PUT. | GET response returns 'hostName'; PUT request body accepts 'hostname'. | Pick one casing and use it in both. Recommend 'hostName' (matches GET and the rest of the spec). | Dev | High | YES - is 'hostname' what firmware actually accepts? | Open
2 | /cloud/region | GET + PUT | getRegion / setRegion | get_region / set_region | Field casing mismatch between GET and PUT (2 fields). | GET returns 'lbtEnabled' + 'channelData'; PUT accepts 'isLBT' + 'channeldata'. | Align to one name per field across GET and PUT. | Dev | High | YES - confirm the firmware key names. | Open
3 | /cloud/region | PUT | setRegion | set_region | 'country' and 'standardname' have no enum and no reference to the list endpoints. | Both are free-text type: string. | Either add an enum, or add a description pointing to GET /cloud/supportedRegionList and GET /cloud/supportedStandardList. | Doc | Medium | No - doc can fix once dev confirms the values are dynamic. | Open
4 | /cloud/certificates/{certname} | DELETE | delCertificate | del_certificate | 'type' is sent in the DELETE request body instead of as a query parameter. | requestBody has properties [type], required [type]. | Move to '?type=' query param (DELETE bodies are widely unsupported), or confirm the firmware genuinely reads a DELETE body. | Dev | High | YES - does the device read a body on DELETE? | Open
5 | /cloud/mode | PUT | setMode | set_mode | Stray / non-API fields still present in the request schema. | Body properties include 'component', 'payload', 'linkProfile' alongside the real mode fields. | Remove 'component' and 'payload' (they look like MQTT envelope fields). Confirm whether 'linkProfile' is real. | Dev | High | YES - are component/payload/linkProfile valid here? | Open
6 | /cloud/mode | PUT | setMode | set_mode | Complex sub-objects appear only in examples, not as schema properties. | 'selects', 'accesses', 'radioStartConditions', 'radioStopConditions', 'modeSpecificSettings' are in the examples but absent from properties. | Point requestBody at the existing operatingMode.v1 component instead of an inline schema. | Dev | High | YES - confirm operatingMode.v1 is the correct contract. | Open
7 | /cloud/status | GET | getStatus | get_status | impinjGen2X field name mismatch: schema says 'active', device returns 'isActive'. | Schema: impinjGen2X.properties = [active, feature]. MQTT tested payload (3 June) returned 'isActive'. | Align schema to device, or fix device output. Already captured in status-schema-followup.md. | Dev | High | YES - which one is the source of truth? | Open - already logged
8 | /cloud/status | GET | getStatus | get_status | impinjGen2X.feature enum does not include the value the device actually returns. | Enum = [fastId, tagFocus, tagProtect, tagQuieting]; the device returned 'none'. | Add 'none' to the enum (device returns it when no Gen2X feature is active). | Dev | High | YES - confirm 'none' is a valid steady-state value. | Open - already logged
9 | /cloud/status | GET | getStatus | get_status | Three response fields still have no description. | 'systemTime', 'temperature', 'uptime' have no description. All nested objects DO now have descriptions. | Add descriptions and units (temperature in degC? uptime format 0D1H13M15S? systemTime format and timezone?). | Doc | Medium | YES - need the units and formats from dev. | Open
10 | /cloud/readerCapabilities | GET | getReadercapabilities | get_readerCapabilities | 25 of the 29 'capabilities' sub-fields have no description. | Missing on numGPIs, numGPOs, llrpSupported, endpointTypesSupported, apiSupported, appLEDColors, maxDataEndpoints, triggers and 17 others. | Add a one-line description per capability field. Dev to explain the non-obvious ones. | Doc | Medium | Partly - dev to explain maxNumPreFilters, maxNumOperationsInAccessSequence, daLanguageBindings. | Open
11 | /cloud/supportedStandardList | GET | getSupportedstandardlist | get_SupportedStandardList | Booleans are returned as strings, and 'channeldata' casing differs from GET /cloud/region. | isLBTConfigurable / isChannelSelectable / isHoppingConfigurable are type: string with enum ['true','false']. | Confirm whether the device really sends the strings true/false. If yes, keep and document. If not, change to real booleans. | Dev | Medium | YES - string or real boolean? | Open
12 | /cloud/supportedStandardList | GET | getSupportedstandardlist | get_SupportedStandardList | 'SupportedStandards' array items lack field-level descriptions. | Item properties are present but undocumented. | Add a description to each item field. | Doc | Low | No | Open
13 | /cloud/impinjGen2X | GET + PUT | getImpinjGen2X / setImpinjGen2X | get/set_impinjGen2X | 'fastID.tidSelector' is missing from the schema. | fastID only has 'enabled'. tidSelector (enum TID[0]-TID[3]) appears in MQTT and in the examples but not in the schema. | Add 'tidSelector' to the fastID object, or confirm it was dropped. | Dev | Medium | YES - is tidSelector still supported? | Open
14 | /cloud/certificates | GET | getCertificates | get_certificates | Confirm the item-level 'type' enum and field descriptions. | Array items expose 'type'; needs confirmation that the enum is exactly [server, client, app]. | Confirm the enum values, then finalise the item descriptions. | Dev | Low | YES - confirm those 3 values are the complete set. | Open
15 | /cloud/certificates | PUT | setUpdatecertificate | set_updateCertificate | The 200 response has no body schema. | 'required' is now correctly [url, type, name]. But the 200 response defines no schema. | Document the success response (empty string? object?). | Dev | Medium | YES - what does a successful install return? | Open
16 | /cloud/eSimConfig | GET | (none - missing) | get_eSimConfig | Response fields 'eid', 'imei', 'profiles' have no descriptions. | Present in the schema but undocumented. NOTE: this operation also has NO operationId - see the OperationId Issues tab. | Add descriptions; explain what EID vs ICCID vs IMEI mean to an integrator. | Doc | Low | No | Open
17 | /cloud/apps | GET | getUserapps | get_userapps | Item-level required fields and array constraints are unconfirmed. | Needs confirmation of minItems / uniqueItems / default [] and which item fields are always present. | Confirm, then finalise. | Doc | Low | YES - is 'metadata' always returned? | Open

## 2. OperationId Issues
OPERATIONID ISSUES - 12 operations have NO operationId; 19 more have casing drift vs the description files
SL | Endpoint | Method | operationId in RestDeveloperfile.yaml | Matching description file | Issue | Proposed Fix | Owner | Status | Dev Notes
1 | /cloud/gpo | GET | *** NONE *** | getGpoStatus.md | Operation has NO operationId at all in the developer file. | Add an operationId. A description file already exists and is waiting to be linked to it. | Dev | Open
2 | /cloud/preSelection | GET | *** NONE *** | getPreSelection.md | Operation has NO operationId at all in the developer file. | Add an operationId. A description file already exists and is waiting to be linked to it. | Dev | Open
3 | /cloud/preSelection | PUT | *** NONE *** | setPreSelection.md | Operation has NO operationId at all in the developer file. | Add an operationId. A description file already exists and is waiting to be linked to it. | Dev | Open
4 | /cloud/logs/syslog | GET | *** NONE *** | getLogsSyslog.md | Operation has NO operationId at all in the developer file. | Add an operationId. A description file already exists and is waiting to be linked to it. | Dev | Open
5 | /cloud/logs/syslog | DELETE | *** NONE *** | delLogsSyslog.md | Operation has NO operationId at all in the developer file. | Add an operationId. A description file already exists and is waiting to be linked to it. | Dev | Open
6 | /cloud/logs/RcLog | GET | *** NONE *** | getRcLog.md | Operation has NO operationId at all in the developer file. | Add an operationId. A description file already exists and is waiting to be linked to it. | Dev | Open
7 | /cloud/logs/RgWarningLog | GET | *** NONE *** | getRgWarningLog.md | Operation has NO operationId at all in the developer file. | Add an operationId. A description file already exists and is waiting to be linked to it. | Dev | Open
8 | /cloud/logs/RgErrorLog | GET | *** NONE *** | getRgErrorLog.md | Operation has NO operationId at all in the developer file. | Add an operationId. A description file already exists and is waiting to be linked to it. | Dev | Open
9 | /cloud/logs/radioPacketLog | GET | *** NONE *** | getRadioPacketLog.md | Operation has NO operationId at all in the developer file. | Add an operationId. A description file already exists and is waiting to be linked to it. | Dev | Open
10 | /cloud/logs/radioPacketLog | DELETE | *** NONE *** | delRadioPacketLog.md | Operation has NO operationId at all in the developer file. | Add an operationId. A description file already exists and is waiting to be linked to it. | Dev | Open
11 | /cloud/ntpServer | GET | *** NONE *** | getNtpServer.md | Operation has NO operationId at all in the developer file. | Add an operationId. A description file already exists and is waiting to be linked to it. | Dev | Open
12 | /cloud/eSimConfig | GET | *** NONE *** | getEsimConfig.md | Operation has NO operationId at all in the developer file. | Add an operationId. A description file already exists and is waiting to be linked to it. | Dev | Open
13 | (see operationId) | - | getGPIStatus | getGpiStatus.md | Casing drift: the developer file uses flat-case, the documentation uses camelCase. | Agree ONE canonical spelling. The docs currently use 'getGpiStatus'. | Dev + Doc | Open
14 | (see operationId) | - | getNetworkinterfaces | getNetworkInterfaces.md | Casing drift: the developer file uses flat-case, the documentation uses camelCase. | Agree ONE canonical spelling. The docs currently use 'getNetworkInterfaces'. | Dev + Doc | Open
15 | (see operationId) | - | getReadpoints | getReadPoints.md | Casing drift: the developer file uses flat-case, the documentation uses camelCase. | Agree ONE canonical spelling. The docs currently use 'getReadPoints'. | Dev + Doc | Open
16 | (see operationId) | - | getSupportedregionlist | getSupportedRegionList.md | Casing drift: the developer file uses flat-case, the documentation uses camelCase. | Agree ONE canonical spelling. The docs currently use 'getSupportedRegionList'. | Dev + Doc | Open
17 | (see operationId) | - | getTimezone | getTimeZone.md | Casing drift: the developer file uses flat-case, the documentation uses camelCase. | Agree ONE canonical spelling. The docs currently use 'getTimeZone'. | Dev + Doc | Open
18 | (see operationId) | - | getUserapps | getUserApps.md | Casing drift: the developer file uses flat-case, the documentation uses camelCase. | Agree ONE canonical spelling. The docs currently use 'getUserApps'. | Dev + Doc | Open
19 | (see operationId) | - | localrestlogin | localRestLogin.md | Casing drift: the developer file uses flat-case, the documentation uses camelCase. | Agree ONE canonical spelling. The docs currently use 'localRestLogin'. | Dev + Doc | Open
20 | (see operationId) | - | setAppled | setAppLed.md | Casing drift: the developer file uses flat-case, the documentation uses camelCase. | Agree ONE canonical spelling. The docs currently use 'setAppLed'. | Dev + Doc | Open
21 | (see operationId) | - | setAutostartuserapp | setAutostartUserApp.md | Casing drift: the developer file uses flat-case, the documentation uses camelCase. | Agree ONE canonical spelling. The docs currently use 'setAutostartUserApp'. | Dev + Doc | Open
22 | (see operationId) | - | setCablelosscompensation | setCableLossCompensation.md | Casing drift: the developer file uses flat-case, the documentation uses camelCase. | Agree ONE canonical spelling. The docs currently use 'setCableLossCompensation'. | Dev + Doc | Open
23 | (see operationId) | - | setImportcloudconfig | setImportCloudConfig.md | Casing drift: the developer file uses flat-case, the documentation uses camelCase. | Agree ONE canonical spelling. The docs currently use 'setImportCloudConfig'. | Dev + Doc | Open
24 | (see operationId) | - | setInstalluserapp | setInstallUserApp.md | Casing drift: the developer file uses flat-case, the documentation uses camelCase. | Agree ONE canonical spelling. The docs currently use 'setInstallUserApp'. | Dev + Doc | Open
25 | (see operationId) | - | setOs | setOS.md | Casing drift: the developer file uses flat-case, the documentation uses camelCase. | Agree ONE canonical spelling. The docs currently use 'setOS'. | Dev + Doc | Open
26 | (see operationId) | - | setRefreshcertificate | setRefreshCertificate.md | Casing drift: the developer file uses flat-case, the documentation uses camelCase. | Agree ONE canonical spelling. The docs currently use 'setRefreshCertificate'. | Dev + Doc | Open
27 | (see operationId) | - | setReqtouserapp | setReqToUserApp.md | Casing drift: the developer file uses flat-case, the documentation uses camelCase. | Agree ONE canonical spelling. The docs currently use 'setReqToUserApp'. | Dev + Doc | Open
28 | (see operationId) | - | setStartuserapp | setStartUserApp.md | Casing drift: the developer file uses flat-case, the documentation uses camelCase. | Agree ONE canonical spelling. The docs currently use 'setStartUserApp'. | Dev + Doc | Open
29 | (see operationId) | - | setStopuserapp | setStopUserApp.md | Casing drift: the developer file uses flat-case, the documentation uses camelCase. | Agree ONE canonical spelling. The docs currently use 'setStopUserApp'. | Dev + Doc | Open
30 | (see operationId) | - | setTimezone | setTimeZone.md | Casing drift: the developer file uses flat-case, the documentation uses camelCase. | Agree ONE canonical spelling. The docs currently use 'setTimeZone'. | Dev + Doc | Open
31 | (see operationId) | - | setUninstalluserapp | setUninstallUserApp.md | Casing drift: the developer file uses flat-case, the documentation uses camelCase. | Agree ONE canonical spelling. The docs currently use 'setUninstallUserApp'. | Dev + Doc | Open

## 3. Description Issues
DESCRIPTION ISSUES - RestAPI/operation_descriptions
SL | Area | Issue | Impact | Proposed Fix | Owner | Status | Dev Notes
1 | RestAPI/operation_descriptions (70 files) | 19 description files do not match the operationId in RestDeveloperfile.yaml (casing only). | Descriptions will not attach to the right operation when the spec is built. It looks like 19 'missing' plus 31 'orphan' files, but it is really just one naming disagreement. | Fix once a canonical operationId convention is agreed (see tab 2). No content rewrite needed. | Dev + Doc | Open
2 | RestAPI/operation_descriptions | 12 description files have no operation to attach to, because those operations carry no operationId. | getGpoStatus, getPreSelection, setPreSelection, getLogsSyslog, delLogsSyslog, getRcLog, getRgWarningLog, getRgErrorLog, getRadioPacketLog, delRadioPacketLog, getNtpServer, getEsimConfig. | Dev adds the 12 operationIds; the files then link automatically. | Dev | Open
3 | NTP server description (getNtpServer / updateNtpServer) | AGREED IN CALL (Mayur, 01:02:21): update the NTP server description FIRST as a single sample, then review before rolling out to the rest. | This is the gating item - all the remaining description work waits on this review. | Apply the agreed template to the NTP description only, get Mayur's sign-off, then batch the remainder. | Doc | *** NEXT ACTION ***
4 | All SET command descriptions | Confirm the 4-section template is correct: Description / Command Details / Before You Begin / Rules and Constraints. | Applies to every set_* command. | Confirm the template with Mayur on the NTP sample before mass-applying it. | Doc | Blocked on #3
5 | All DELETE command descriptions | Confirm the simpler DELETE template (bullet-list constraints, no sub-headings, no Security Note). | Applies to del_certificate, delLogsSyslog, delRadioPacketLog. | Confirm with Mayur. | Doc | Blocked on #3
6 | Events | Out of scope - event schemas and definitions are NOT to be modified. | Scope is command/response plus REST only. | No action. Do not touch the event definitions. | - | Closed - agreed

## 4. Decisions Needed
DECISIONS NEEDED FROM DEVELOPER - work through these in the meeting
SL | Question for Developer | Why it matters | Options | Recommendation | Decision | Owner
1 | For hostName and region: which key casing does the FIRMWARE actually accept - 'hostname' or 'hostName'? 'isLBT' or 'lbtEnabled'? 'channeldata' or 'channelData'? | Right now GET and PUT disagree. An integrator who copies the GET response into a PUT will get a failure. | (a) Firmware is right, fix the docs (b) Docs are right, fix the firmware | Make GET and PUT use the SAME key. Prefer the GET spelling: hostName, lbtEnabled, channelData. |  | Dev
2 | Does DELETE /cloud/certificates/{certname} really read 'type' from the request body? | Many HTTP clients and proxies drop DELETE bodies, so this may be silently broken for some users. | (a) Move to ?type= query param (b) Keep the body and document the limitation | Move it to a query parameter. |  | Dev
3 | For GET /cloud/status - is 'active' or 'isActive' correct? And is 'feature: none' a valid value? | The tested device (3 June) returned 'isActive' and 'feature: none'; the schema says 'active' with no 'none'. | (a) Schema follows the device (b) Device follows the schema | Schema follows the device: rename to 'isActive' and add 'none' to the enum. |  | Dev
4 | Are 'component', 'payload' and 'linkProfile' valid fields on PUT /cloud/mode? | component and payload look like MQTT envelope fields that leaked into the REST body. | (a) Remove them (b) Keep them - they are real | Remove component and payload; confirm linkProfile separately. Point the body at operatingMode.v1. |  | Dev
5 | Does GET /cloud/supportedStandardList really return 'true'/'false' as STRINGS? | The schema documents string-encoded booleans, which is unusual and awkward for clients. | (a) Yes - keep and document (b) No - they should be real booleans | If it is a bug, fix it to real booleans now, before customers depend on it. |  | Dev
6 | Is 'fastID.tidSelector' (TID[0]-TID[3]) still supported? | It appears in MQTT and in the examples but is absent from the schema. | (a) Add it to the schema (b) Deprecated - remove it from the examples | Confirm, then make the schema and examples agree. |  | Dev
7 | What is the canonical operationId convention - 'setOs' or 'setOS'? 'getTimezone' or 'getTimeZone'? | 19 operations disagree between the developer file and the description files. | (a) camelCase (getTimeZone, setOS) (b) flat-case (getTimezone, setOs) | camelCase - it matches the docs and the majority of the existing spec. |  | Dev + Doc
8 | Will you add operationIds to the 12 operations that currently have none? | 12 already-written description files cannot attach to anything until this is done. | (a) Dev adds them (b) Doc proposes them and dev approves | Doc proposes the 12 names, dev approves them in one pass. |  | Dev
9 | Units and formats for GET /cloud/status: temperature, uptime, systemTime. | Accurate descriptions cannot be written without them. | e.g. temperature in degC? uptime as 0D1H13M15S? systemTime timezone? | Dev confirms; doc writes them up. |  | Dev